SIMS Ghana

School Information Management System

Development Roadmap & Sprint Plan

Version 1.0 | January 2026

Author: Harry McNinson

# 1. Executive Summary

This document outlines the development roadmap for SIMS Ghana, structured into phases and sprints. The plan targets a 12-month development cycle with an MVP launch at 6 months.

## 1.1 Project Timeline Overview

| Phase | Duration | Timeline | Goal |
| --- | --- | --- | --- |
| Phase 1 | 3 months | Jan - Mar 2026 | Foundation & Core |
| Phase 2 | 3 months | Apr - Jun 2026 | MVP Launch |
| Phase 3 | 3 months | Jul - Sep 2026 | Enhancement |
| Phase 4 | 3 months | Oct - Dec 2026 | Scale & Mobile |

## 1.2 Team Structure (Recommended)

| Role | Count | Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Coordination, stakeholder communication, timeline |
| Tech Lead / Architect | 1 | Architecture decisions, code review, mentoring |
| Backend Developers | 2-3 | FastAPI, PostgreSQL, integrations |
| Frontend Developers | 2 | Next.js, React, UI implementation |
| Mobile Developer | 1 | React Native (Phase 4) |
| UI/UX Designer | 1 | Wireframes, prototypes, design system |
| QA Engineer | 1 | Testing, automation, quality assurance |
| DevOps Engineer | 1 | Infrastructure, CI/CD, deployment |

## 1.3 Key Milestones

| Milestone | Target Date | Deliverables |
| --- | --- | --- |
| M1: Alpha Release | Mar 2026 | Core modules working, internal testing |
| M2: Beta Release | May 2026 | Full MVP features, pilot schools |
| M3: MVP Launch | Jun 2026 | Public launch, first paying customers |
| M4: Mobile Apps | Dec 2026 | iOS/Android apps in stores |

# 2. Phase 1: Foundation & Core (Jan - Mar 2026)

Phase 1 focuses on setting up infrastructure, core architecture, and essential modules.

## Sprint 1 (Weeks 1-2): Project Setup

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 1.1 | Set up Git repository, branching strategy | DevOps | 3 |
| 1.2 | Set up FastAPI project structure | Tech Lead | 5 |
| 1.3 | Set up Next.js 16 project with App Router | Frontend | 5 |
| 1.4 | Configure PostgreSQL, create initial migrations | Backend | 5 |
| 1.5 | Set up Docker Compose for local dev | DevOps | 3 |
| 1.6 | Configure CI/CD pipeline (GitHub Actions) | DevOps | 5 |
| 1.7 | Set up staging environment on AWS | DevOps | 8 |
| 1.8 | Design system setup (Tailwind, Shadcn) | Designer | 5 |

## Sprint 2 (Weeks 3-4): Authentication & Multi-Tenancy

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 2.1 | Implement tenant model and RLS policies | Backend | 8 |
| 2.2 | User registration and email verification | Backend | 5 |
| 2.3 | JWT authentication with refresh tokens | Backend | 8 |
| 2.4 | Role-based access control (RBAC) | Backend | 8 |
| 2.5 | Login/Register UI pages | Frontend | 5 |
| 2.6 | Password reset flow | Full Stack | 5 |
| 2.7 | Subdomain tenant detection middleware | Backend | 5 |
| 2.8 | Auth API integration tests | QA | 3 |

## Sprint 3 (Weeks 5-6): School Setup & Academic Structure

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 3.1 | School profile CRUD | Backend | 5 |
| 3.2 | Academic year management | Backend | 5 |
| 3.3 | Term management | Backend | 3 |
| 3.4 | Classes and sections CRUD | Backend | 5 |
| 3.5 | Subjects management | Backend | 5 |
| 3.6 | School setup wizard UI | Frontend | 8 |
| 3.7 | Academic structure UI (classes, subjects) | Frontend | 8 |
| 3.8 | Dashboard layout and navigation | Frontend | 5 |

## Sprint 4 (Weeks 7-8): Student Management

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 4.1 | Student CRUD API | Backend | 8 |
| 4.2 | Guardian management | Backend | 5 |
| 4.3 | Student-guardian relationships | Backend | 3 |
| 4.4 | Class enrollment API | Backend | 5 |
| 4.5 | Student list UI with search/filter | Frontend | 8 |
| 4.6 | Student profile/detail page | Frontend | 5 |
| 4.7 | Add/Edit student form | Frontend | 8 |
| 4.8 | Bulk student import (Excel) | Full Stack | 8 |
| 4.9 | Photo upload functionality | Full Stack | 5 |

## Sprint 5 (Weeks 9-10): Staff & User Management

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 5.1 | Staff CRUD API | Backend | 8 |
| 5.2 | Teacher-subject-class assignments | Backend | 5 |
| 5.3 | User management (invite, disable) | Backend | 5 |
| 5.4 | Role management UI | Frontend | 5 |
| 5.5 | Staff list and profile UI | Frontend | 8 |
| 5.6 | User invitation flow | Full Stack | 5 |
| 5.7 | Permission assignment UI | Frontend | 5 |

## Sprint 6 (Weeks 11-12): Attendance Module

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 6.1 | Student attendance API | Backend | 8 |
| 6.2 | Bulk attendance marking | Backend | 5 |
| 6.3 | Attendance reports API | Backend | 5 |
| 6.4 | Daily attendance marking UI | Frontend | 8 |
| 6.5 | Attendance history view | Frontend | 5 |
| 6.6 | SMS notification for absence | Backend | 5 |
| 6.7 | Offline attendance (PWA) | Frontend | 8 |
| 6.8 | Attendance reports UI | Frontend | 5 |

# 3. Phase 2: MVP Launch (Apr - Jun 2026)

Phase 2 completes core functionality for MVP and launches to pilot schools.

## Sprint 7 (Weeks 13-14): Exams & Grading

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 7.1 | Exam/assessment CRUD API | Backend | 5 |
| 7.2 | Score entry API | Backend | 8 |
| 7.3 | Grading scale configuration | Backend | 5 |
| 7.4 | Grade calculation engine | Backend | 8 |
| 7.5 | Exam management UI | Frontend | 5 |
| 7.6 | Score entry UI (by subject) | Frontend | 8 |
| 7.7 | Bulk score import (Excel) | Full Stack | 8 |
| 7.8 | Class rankings calculation | Backend | 5 |

## Sprint 8 (Weeks 15-16): Report Cards

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 8.1 | Report card data aggregation API | Backend | 8 |
| 8.2 | Report card template engine | Backend | 8 |
| 8.3 | PDF generation (WeasyPrint) | Backend | 8 |
| 8.4 | QR code verification | Backend | 3 |
| 8.5 | Report card preview UI | Frontend | 5 |
| 8.6 | Bulk report card generation | Full Stack | 5 |
| 8.7 | Teacher remarks entry | Frontend | 5 |
| 8.8 | Report card template customization | Full Stack | 8 |

## Sprint 9 (Weeks 17-18): Finance - Fee Structure & Invoicing

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 9.1 | Fee categories and structures API | Backend | 5 |
| 9.2 | Invoice generation engine | Backend | 8 |
| 9.3 | Bulk invoice generation | Backend | 5 |
| 9.4 | Invoice PDF generation | Backend | 5 |
| 9.5 | Fee structure setup UI | Frontend | 5 |
| 9.6 | Invoice list and detail UI | Frontend | 8 |
| 9.7 | Student billing view | Frontend | 5 |
| 9.8 | Discounts and scholarships | Full Stack | 5 |

## Sprint 10 (Weeks 19-20): Finance - Payments & Mobile Money

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 10.1 | Cash payment recording | Backend | 5 |
| 10.2 | MTN MoMo API integration | Backend | 13 |
| 10.3 | Payment webhook handling | Backend | 8 |
| 10.4 | Receipt generation | Backend | 5 |
| 10.5 | Payment recording UI | Frontend | 5 |
| 10.6 | MoMo payment initiation UI | Frontend | 8 |
| 10.7 | Payment history and reconciliation | Full Stack | 8 |
| 10.8 | Outstanding fees dashboard | Frontend | 5 |

## Sprint 11 (Weeks 21-22): Communication & Notifications

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 11.1 | SMS gateway integration (Hubtel) | Backend | 8 |
| 11.2 | SMS templates and bulk sending | Backend | 5 |
| 11.3 | Announcement system | Backend | 5 |
| 11.4 | Email notifications (SendGrid) | Backend | 5 |
| 11.5 | SMS credit management | Full Stack | 5 |
| 11.6 | Announcement UI | Frontend | 5 |
| 11.7 | Notification center UI | Frontend | 5 |
| 11.8 | SMS delivery reports | Full Stack | 3 |

## Sprint 12 (Weeks 23-24): MVP Polish & Beta Launch

| ID | Task | Owner | Story Pts |
| --- | --- | --- | --- |
| 12.1 | Dashboard analytics and charts | Full Stack | 8 |
| 12.2 | Basic reports (enrollment, attendance) | Full Stack | 8 |
| 12.3 | Parent portal (view-only) | Full Stack | 8 |
| 12.4 | Bug fixes and optimization | All | 13 |
| 12.5 | Security audit and penetration testing | QA/DevOps | 8 |
| 12.6 | Performance optimization | All | 8 |
| 12.7 | Documentation and help guides | PM | 5 |
| 12.8 | Beta launch to pilot schools (3-5) | All | 5 |

# 4. Phase 3: Enhancement (Jul - Sep 2026)

Phase 3 adds advanced features based on beta feedback.

## Sprint 13-14: Boarding Management

| Feature | Details |
| --- | --- |
| Dormitory & Room Management | CRUD, capacity tracking |
| Bed Assignments | Student room/bed allocation |
| Exeat Management | Request, approval, tracking |
| Roll Calls | Morning, evening, lights-out |
| Sick Bay Records | Health tracking |

## Sprint 15-16: Transport Management

| Feature | Details |
| --- | --- |
| Vehicle Fleet | Registration, maintenance tracking |
| Route Management | Routes, stops, schedules |
| Student Assignments | Route/stop assignments |
| Transport Fees | Fee integration |

## Sprint 17-18: Enrollment & Admissions

| Feature | Details |
| --- | --- |
| Online Applications | Public application form |
| Application Processing | Review, shortlist, accept |
| Entrance Exams | Scheduling, scoring |
| Enrollment Workflow | Admission to enrollment |
| Re-enrollment | Annual re-enrollment process |

# 5. Phase 4: Scale & Mobile (Oct - Dec 2026)

Phase 4 focuses on mobile apps, advanced features, and scaling.

## Sprint 19-22: Mobile Applications

| Deliverable | Details |
| --- | --- |
| Parent Mobile App (React Native) | View grades, fees, attendance, pay via MoMo |
| Teacher Mobile App | Mark attendance, enter grades, view schedule |
| Push Notifications | Firebase Cloud Messaging integration |
| Offline Sync | WatermelonDB for offline data |
| App Store Deployment | iOS App Store, Google Play Store |

## Sprint 23-24: Advanced Features & Scaling

| Feature | Details |
| --- | --- |
| Multi-Curriculum Support | Cambridge, IB, American alongside GES |
| Preschool Module | Developmental milestones, daily activities |
| Asset & Inventory | Asset tracking, stock management |
| Advanced Analytics | Custom reports, dashboards |
| GES/WAEC Integration | Census export, exam registration |
| Chain Management | Multi-school consolidated features |

# 6. Risk Management

| Risk | Impact | Mitigation | Contingency |
| --- | --- | --- | --- |
| MoMo API delays | High | Early sandbox testing | Support bank transfer first |
| Scope creep | Medium | Strict backlog management | Phase shifting |
| Developer turnover | High | Documentation, pair programming | Cross-training |
| Poor beta feedback | Medium | Early user involvement | Rapid iteration |
| Performance issues | High | Load testing from Sprint 10 | Optimization sprint |
| Security vulnerabilities | Critical | Regular security audits | Bug bounty program |

# 7. Budget Estimates

Rough estimates for 12-month development (Ghana-based team):

| Category | Monthly (GHS) | Annual (GHS) |
| --- | --- | --- |
| Development Team (8-10 people) | 120,000 | 1,440,000 |
| AWS Infrastructure | 5,000 | 60,000 |
| Third-party Services (SMS, etc.) | 2,000 | 24,000 |
| Tools & Licenses | 1,500 | 18,000 |
| Contingency (15%) | - | 231,000 |
| TOTAL | - | 1,773,000 |

Note: Approximately $140,000 USD at current exchange rates. Costs may vary based on team experience and location.

# 8. Document History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | January 2026 | Harry McNinson | Initial version |